## Portfolio Analysis
Portfolio Analysis Workshops
| Start Time | Duration Minutes | Topic | Application Owners | Application Developers | Cloud Programme Owner | Enterprise Architect(s) | Application Architect(s) | Cloud Platform Lead | Cloud Platfrom SMEs | On-prem platform SMEs | On-prem Networks SMEs | InfoSec | Third-Parties
Day 1 | 9:00 | 30 | Opening / Goal Setting Objectives: 1/Alignment. 2/Goals for the day. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 9:30 | 60 | Asset & Dependency Discovery Output Review Objectives: High-level review of the data collected by the discovery tool and/or data available from CMDBs and other sources | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 10:30 | 90 | Review/Validate Application Stacks - part 1 Important Note: Whenever possible, ensure that available automated processes to generate application stacks in the Discovery Tool of choice are performed in advance. This is in order to avoid waiting times during the workshop. Objectives: 1/Review/Validate application stacks identified by discovery tooling or those provided by customer. 2/ Validate applications to infrastructure mapping. 3/ Identify high-level migration data requirements (e.g., criticality, business function, key dependencies). 4/Document application information. 5/ Identify Complex Applications (i.e., Big Rocks) | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 12:00 | 45 | Launch Break
| 12:45 | 120 | Review/Validate Application Stacks - part 2 Objectives: Continue from part 1 | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 14:45 | 15 | Break
| 15:00 | 90 | Review/Validate Application Stacks - part 3 Objectives: Continue from part 2 | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 16:30 | 30 | Wrap-up Objectives: Review outcomes of the day and next steps (e.g., adhoc sessions to iterate/finalize elements of the agenda) | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
Day 2 | 9:00 | 30 | Opening / Goal Setting Objectives: Goals for the day. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 9:30 | 120 | 7R Disposition Tree Objectives: 1/ Review/update 7R definitions and agree to a common language. 2/Update the 7R disposition Tree based on known customer business drivers, architecture and technology aspects. Note: This is a first approach at updating the tree, it will require subsequent iterations as more data becomes available. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Opt. | Req. | as needed
| 11:30 | 60 | Iterate Application Prioritization Criteria Objectives: 1/ Upload Application Data to MPA and Establish weighting to identified prioritization attributes to determine application prioritization (i.e., the order in which applications will be migrated) based on customer outcomes. 2/ Validate Wave 1 (or pilot apps) candidates | Req. | Opt. | Req. | Req. | Req. | Req. | Opt. | Opt. | Opt. | Req. | as needed
| 12:30 | 45 | Launch Break
| 13:15 | 60 | Validate Wave 1 (or pilot apps) candidates Objectives: Confirm candidates for Wave 1 or Pilot Apps based on appliation prioritization criteria or customer preference | Req. | Opt. | Req. | Req. | Req. | Req. | Opt. | Opt. | Opt. | Req. | as needed
| 14:15 | 60 | Initial Wave Planning - Part 1 Objectives: Outline a first draft of a Wave Plan (see Wave Planning page in the delivery kit) considering dates and desired outcomes. This will be the base to keep iterating a Wave Plan. | Opt. | Opt. | Req. | Req. | Opt. | Req. | Opt. | Opt. | Opt. | Opt. | as needed
| 15:15 | 15 | Break
| 15:30 | 60 | Initial Wave Planning - Part 2 Objectives: Continue from part 1 | Opt. | Opt. | Req. | Req. | Opt. | Req. | Opt. | Opt. | Opt. | Opt. | as needed
| 16:30 | 30 | Wrap-up Objectives: Review of outcomes and next steps | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed